## Subject Set Tracker
Zooniverse Subject Set Tracker
Track transects, subject sets, image counts, upload status & script versions
Transect ID | Site / Survey Area | Date Surveyed | Subject Set Name | Subject Set ID | # Images | # Subjects uploaded | Upload Date | Export Date | Export File Name | Status | Notes
CNL_S24_T1 | Elliott Bay / Centennial | 2024-10-08 | [8 empty] | Not done in Zooniverse
CNL_S24_T2 | Elliott Bay / Centennial | 2024-10-08 | [8 empty] | Not done in Zooniverse
CNL_S24_T3 | Elliott Bay / Centennial | 2024-10-08 | [8 empty] | Not done in Zooniverse
CNL_S24_T4 | Elliott Bay / Centennial | 2024-10-08 | [8 empty] | Not done in Zooniverse
CNL_S24_T5 | Elliott Bay / Centennial | 2024-10-08 | [8 empty] | Not done in Zooniverse
CNL_S24_T6 | Elliott Bay / Centennial | 2024-10-08 | [8 empty] | Not done in Zooniverse
EBM_S24_T1 | Elliott Bay / EBM | 2024-10-09 | [8 empty] | Not done in Zooniverse
EBM_S24_T2 | Elliott Bay / EBM | 2024-10-09 | [8 empty] | Not done in Zooniverse
EBM_S24_T3 | Elliott Bay / EBM | 2024-10-09 | [8 empty] | Not done in Zooniverse
EBM_S24_T4 | Elliott Bay / EBM | 2024-10-09 | [8 empty] | Not done in Zooniverse
EBM_S24_T4 | Elliott Bay / EBM | 2024-10-09 | [8 empty] | Not done in Zooniverse
EBM_S24_T6 | Elliott Bay / EBM | 2024-10-09 | [8 empty] | Not done in Zooniverse
CNL_W25_T1 | Elliott Bay / Centennial | 2025-01-27 | 2025_01_27_Centennial_T1 | 135009 | 66 | 3100 | 2026-03-24 |  |  | Complete | Classification model EB_HSIL_2025_01_19
CNL_W25_T4 | Elliott Bay / Centennial | 2025-01-27 | 2025_01_27_Centennial_T4 | 135018 | 71 | 3350 | 2026-03-24 |  |  | Complete | Classification model EB_HSIL_2025_01_19
EBM_W25_T1 | Elliott Bay / EBM | 2025-01-28 | 2025_01_28_EBM_T1 | 135048 | 64 | 3000 | 2026-03-24 |  |  | Complete | Classification model EB_HSIL_2025_01_19
EBM_W25_T4 | Elliott Bay / EBM | 2025-01-28 | 2025_01_28_EBM_T4 | 135054 | 62 | 2900 | 2026-03-24 |  |  | Complete | Classification model EB_HSIL_2025_01_19
CNL_W25_T5 | Elliott Bay / Centennial | 2025-01-27 | 2025_01_27_Centennial_T5 | 135378 | 66 | 3300 | 2026-04-05 |  |  | Complete | Classification model EB_HSIL_2025_01_19
EBM_W25_T5 | Elliott Bay / EBM | 2025-01-28 | 2025_01_28_EBM_T5 | 135306 | 56 | 2800 | 2026-04-03 |  |  | Complete | Classification model EB_HSIL_2025_01_19
CNL_W25_T2 | Elliott Bay / Centennial | 2025-01-27 | 2025_01_27_Centennial_T2 | 135393 | 60 | 3000 | 2026-04-06 |  |  | Complete | Classification model EB_HSIL_2025_01_19
EBM_W25_T2 | Elliott Bay / EBM | 2025-01-28 | 2025_01_28_EBM_T2 | 135399 | 60 | 3000 | 2026-04-06 |  |  | Complete | Classification model EB_HSIL_2025_01_19
CNL_W25_T6 | Elliott Bay / Centennial | 2025-01-27 | 2025_01_27_Centennial_T6 | 135757 | 64 | 3200 | 2026-04-20 |  |  | Complete | Classification model EB_HSIL_2025_01_19
EBM_W25_T6 | Elliott Bay / EBM | 2025-01-28 | 2025_01_28_EBM_T6 | 135765 | 58 | 2900 | 2026-04-20 |  |  | Complete | Classification model EB_HSIL_2025_01_19
CNL_W25_T3 | Elliott Bay / Centennial | 2025-01-27 | 2025_01_27_Centennial_T3 | 135910 | 60 | 3000 | 2026-04-23 |  |  | Complete | Classification model EB_HSIL_2025_01_19
EBM_W25_T3 | Elliott Bay / EBM | 2025-01-28 | 2025_01_28_EBM_T3 | 135913 | 58 | 2900 | 2026-04-23 |  |  | Complete | Classification model EB_HSIL_2025_01_19
FPR_S25_T1 | Elliot Bay/ Fishing Pier | 2025-10-08 | FPR_S25_T1 | 136807 | 58 | 2800 | 2026-05-27 |  |  | Complete | Classification model EB_HSIL_2025_01_19
FPR_S25_T2 | Elliot Bay/ Fishing Pier | 2025-10-08 | FPR_S25_T2 | 136811 | 67 | 3350 | 2026-05-27 |  |  | Complete | Classification model EB_HSIL_2025_01_19
FPR_S25_T3 | Elliot Bay/ Fishing Pier | 2025-10-08 | FPR_S25_T3 | 136817 | 82 | 4100 | 2026-05-27 |  |  | Complete | Classification model EB_HSIL_2025_01_19
PKB_S25_T1 | Elliott Bay / Pocket Beach | 2025-08-14 | PKB_S25_T1 | 137510 | 70 | 3500 | 2026-07-08 |  |  | In Progress | Classification model EB_HSIL_2025_01_19, patch size 4.5x
PKB_S25_T3 | Elliott Bay / Pocket Beach | 2025-08-14 | PKB_S25_T3 | 137718 | 79 | 3750 | 2026-07-10 |  |  | In Progress | Classification model EB_HSIL_2025_01_19, patch size 4.5x
PKB_S25_T5 | Elliott Bay / Pocket Beach | 2025-08-14 | PKB_S25_T5 | 138056 | 79 | 3950 | 2026-08-01 |  |  | In Progress | Classification model EB_HSIL_2025_01_19, patch size 4.5x
PKB_S25_T2 | Elliott Bay / Pocket Beach | 2025-08-14 | PKB_S25_T2 | 138908 | 60 | 3000 | 2026-09-13 |  |  | In Progress | Classification model EB_HSIL_2025_01_19, patch size 4.5x

## Export Log
📦 Classification Export Log
Track every classification export download from Zooniverse
Export Date | Exported By | Workflow Name | Workflow ID | Subject Set(s) | # Classifications | # Subjects Retired | Export File Name | Storage Location | Notes
2025-12-01 | J. Smith | Coral ID Workflow | 9876 | NorthBay_Nov2025 | 1480 | 120 | NorthBay_Nov2025_export.csv | exports/2025-12/ | First complete export

## Summary Dashboard
📊 Project Summary Dashboard
Total Transects | 30 | Last Updated
2026-09-13
Total Images Uploaded | 1240
Status Legend
Subject Sets Created | 60900 | Complete
In Progress
Complete | 15 | Awaiting Export
Not Uploaded
In Progress | 4 | On Hold
Awaiting Export | 0
Not Uploaded | 0